# 🚀 BeyondSunday – Structured Phases (2026)

# Phase 1: Foundation Clarity (1–2 weeks)

(You skipped this, but everything depends on it)

Goal:
Define exactly what BeyondSunday is and what you’re building first.

Actions:

- Write:

  - 1-sentence mission

  - 1 core problem

  - 1 core feature (MVP)

- Define target user (be specific, not “everyone”)

- Decide what success looks like for the MVP

Done when:

- You can explain BeyondSunday in 30 seconds clearly

- You have a simple MVP definition

## 🧪  User Feedback Completion (Critical)

(This is your missing piece—now formalised)

Deadline: Within 2 weeks (runs immediately)

Goal:
Reach 20 total user feedback interviews to validate and shape your MVP.

### Current Status

- You already have: 15 interviews

- Remaining: 5 interviews

### Specific Actions (for last 5):

- Prioritise high-probability participants:

  - Close friends

  - Trusted contacts (e.g. Nitish, Monisha)

- Message them directly (not passively)

- Offer clear incentive (prize/reward)

### Execution Rules

- Schedule all 5 within 7–10 days

- Conduct interviews digitally (quick + efficient)

- Keep each session:

  - 15–30 minutes max

  - Focused on core problem + reaction to prototype

### What You’re Extracting (IMPORTANT)

From these 20 interviews, you must identify:

- Top 3 repeated problems

- What users actually care about vs what you assumed

- What part of your prototype they:

  - Understand instantly

  - Find confusing

  - Get excited about

### Achievability Check

👉 If you can’t get 5 people:

- Your network outreach is too weak → fix this now
(not later in visibility phase)

### Done when:

- You have:

  - 20 completed interviews

  - Notes documented

  - Clear patterns identified

## Phase 2: MVP Goes Public (4–8 weeks)

(This connects to your earlier goal)

Goal:
Launch a simple, public version of BeyondSunday.

Actions:

- Work with ex-colleague (or alternative dev)

- Build ONLY core feature

- Deploy:

  - Basic website

  - Working functionality OR clear demo

- Add simple explanation + contact/signup

Done when:

- You can send someone a link and say:
“Try BeyondSunday here”

## Phase 3: *Cofounder Discovery & Validation (Ongoing, structured)

(Refined version of your #1)

Goal:
Find 1 committed, long-term cofounder aligned with mission.

System (not vague effort):

- Attend 1 networking environment every 2 weeks

  - 1.Events, 2. church, 3. work, 4. founder communities

- Have at least 1 follow-up meeting per week after handing business card and connecting

Cofounder Filter (non-negotiable):

- Shares mission deeply (not just interest)

- Shows consistent action, not just talk

- Understands scale + long-term commitment

- Has a clear skill advantage (tech, growth, etc.)

Add a new sub-phase:

### Phase 3A: Collaboration Testing (VERY important)

Before calling anyone cofounder:

Actions:

- Do a 2–4-week trial project together

- Observe:

  - Do they follow through?

  - Do they think independently?

  - Do they care without being pushed?

Done when:

- You either:

  - Commit to them as cofounder

  - OR clearly reject and move on

👉 This prevents the #1 startup mistake: wrong cofounder.

Phase 4

(A)Once secured cofounder, sort out contractual obligations (I.e.: NDA)

## Phase 5: First Visibility Engine (“First Conversation”)

(Refined + broken down version of your #2)

You’re right:

If you don’t have visibility, nothing else matters.

But visibility needs structure:

### Phase 5A: Foundational Presence (2–3 weeks)

Goal:
Make BeyondSunday discoverable and credible.

Actions:

- Launch:

  - Landing page

  - Simple explanation

- Create:

  - Basic social presence (1 platform only to start)

- Update founder platforms (e.g. Foundership)

Done when:

- Someone can:

  - Find you

  - Understand you

  - Follow you

### Phase 5B: Content & Voice (4–8 weeks ongoing)

Goal:
Start “the first conversation” with your audience.

Actions:

- Post 2–3 short videos per week

  - You (and future cofounder)

  - Talk about:

    - Problem

    - Vision

    - Insights

- Keep it simple, not polished

Done when:

- You’ve posted 20+ pieces of content

- You’re getting any engagement (even small)

### Phase 5C: Leverage & Amplification

Goal:
Reach larger audiences faster.

Actions:

- Reach out to:

  - Christian content creators

  - Niche communities

- Do:

  - Interviews (follow up with Eki)

  - Event stalls (once MVP exists)

Done when:

- You’ve done:

  - 3+ collaborations/interviews

  - 1+ real-world showcase

## Phase 6: Early Team Build (Your #3, but tighter)

Goal:
Bring in 1–2 high-quality contributors (not random people).

Roles to prioritise:

- Technical (if not covered)

- OR growth/marketing

Actions:

- Recruit from:

  - People already engaging with you

  - Your network (work/church/events)

  - Surrey foundership

- Start with:

  - Clear roles

  - Small responsibilities

Important rule:
👉 Don’t recruit before visibility starts
(or you’ll attract the wrong people)

Done when:

- At least 1 reliable person contributing weekly

Phase 7

(A)Once secured additional members, sort out contractual obligations (I.e.: NDA) as well as roles with objectives going forward being set in stone

## Phase 8: Core Team Formation (Your #4, refined)

Goal:
Build a small, serious team heading into 2027

Actions:

- Identify:

  - Who consistently shows up

- Formalise:

  - Roles

  - Expectations

- Align on:

  - Vision

  - Long-term commitment

Team size:

- 2–4 people max

Done when:

- You have a tight, committed group actively building

Startup plan (Until 20th December) – Now the startup ball is rolling, it’s time to go from the conceptual phase to then bringing the company to reality (* = most challenging phase)

- Ensure SMART goals truly are Achievable (A) and SPECIFIC on how you will achieve each goal and when by, just like how your first plan was structured (which all objectives were achieved successfully and for the most part in the timeframe). If you don’t feel like you can put an (A) next to it, it means you must explore further how this goal is going to be achievable within the given timeframe)

Phase 2

(A)Make an early version of BeyondSunday accessible on public domain (Ex-colleague is as an option here and is more trustworthy to get this job done right for this) – Phase complete when you can send someone a link and say:
“Try BeyondSunday here” potentially on website

By June

Phase 1

(A)Conduct last 5 interviews to reach goal of 20x feedback to develop MVP from, then award prizes (Ask close friends if they would be open to it, and share with others to get last five (i.e.: Nitish, Monisha) – higher likelihood that they will win. prize

Phase 6*

(A)Secure additional members (at least 1) to work on BeyondSunday coding (app development), marketing, BMC, potential pivot etc..

Phase 3*

(A)Secure a committed and long-term cofounder by going to networking events at least once every two weeks or through other means such as from work or Church or potentially elsewhere, think outside the box – have meetings with those interested in joining/collaborating afterwards – do they share same purpose? Are they committed to the mission? Do they understand its potential scale and impact? Are they permanent or on and off?

Phase 4

(A)Once secured cofounder, sort out contractual obligations (I.e.: NDA)

Phase 5

(A)*Maximise visibility, the first conversation*(multiple phases wihin this) – update founder ship once BeyondSunday becomes available on public domain to get access to stalls at events to showcase BeyondSunday, do interviews (follow up with Eki), debate on creating a social media account where you (and potentially cofounder) post videos of yourselves, reach out to big Christan content creators in space for promo. – Note – if you don’t have visibility, forget everything else – what are we going to do to become visible?

Be aware in this plane, multiple phases can be executed simultaneously, but they do have a deadline

Phase 8

(A)Startup owners will work with other people smarter than them – There will be a small group will be actively working on BeyondSunday going into 2027

Phase 7

(A)Once secured additional members, sort out contractual obligations (I.e.: NDA) as well as roles with objectives going forward being set in stone

By December 20th